## Status
RIVA128 to do:
Task
Class 001 methods | The beta factor is not used
Class 002 methods | Seems fine, ALWAYS CHECK FOR BUGS
Class 003 methods | The chroma key set is not tested
Class 004 methods | NONE
Class 005 methods | NONE
Class 006 methods | Seems fine, ALWAYS CHECK FOR BUGS
Class 007 methods | Seems fine, ALWAYS CHECK FOR BUGS
Class 008 methods | NONE
Class 009 methods | NONE
Class 00a methods | NONE
Class 00b methods | NONE
Class 00c methods | NONE
Class 00d methods | NONE
Class 00e methods | NONE
Class 010 methods | It does at least partially work, but some junk gets sent to the top of the screen
Class 011 methods | Seems fine, ALWAYS CHECK FOR BUGS
Class 012 methods | NONE
Class 014 methods | NONE
Class 015 methods | NONE
Class 017 methods | NONE
Class 018 methods | NONE
Class 01c methods | Maybe done, verify!
Runout | Seems fine, ALWAYS CHECK FOR BUGS
Fix remaining FIFO bugs | Some fixed, there are probably still bugs
DMA Engine
Mediaport
3D Core (TODO: Research)
Notifier Engine | Hardware works, software untested
Cleanup code
Dumb Framebuffer (DFB)
Cursor (RAMDAC_CU) | There is special hardware support, but it just renders anyway using Class 011? At least emulate starting pos
Chroma Key | In progress
Pattern | In progress
Unify position/size structs
Code cleanup

## Bugs
Bugs - last updated 22 March 2025 | Status
"1000Hz" in VESA text mode
1280x1024x16bpp and higher fucked up (wrong resolution set, totally wrong rendering)
8bpp doesn't do crap
VESA: Mode X is broken (DOOM, Boulderoid)
VESA: DOOM is broken
Windows 9x: card not detected
32bpp BSOD on windows 2000
Windows XP Failures
Random Blits end up in the middle of the screen?!
AGP broken
ZX broken

## Resolution
Resolution Testing - RIVA 128 (very very early v0.6) | Resolution | Bitdepth | Result (Win2000) | Result (WinXP)
| 640x480 | 8 | NOT WORKING
| 800x600 | 8 | NOT WORKING
| 640x480 | 16 | WORKING (as much as is implemented)
| 800x600 | 16 | WORKING (as much as is implemented)
| 1024x768 | 16 | WORKING (as much as is implemented)
| 1152x864 | 16 | WORKING (as much as is implemented)
| 1280x1024 | 16 | SORTA WORKING (very screwed up rendering)
| 1600x1200 | 16 | BSOD nv3_mini+0x164c3
| 640x480 | 32 | BSOD win32k+13c692 (CHECK CALLSTACK)
| 800x600 | 32 | BSOD win32k+13c692 (CHECK CALLSTACK)
| 1024x768 | 32 | BSOD win32k+13c692 (CHECK CALLSTACK) | WORKING (as much as is implemented)
| 1152x864 | 32 | BSOD win32k+13c692 (CHECK CALLSTACK)

## Bus
Bus Testing - last updated 22 March 2025 | Bus | Result
| PCI | WORKING
| AGP | NOT WORKING

## App Compatibility - VESA
VESA Compatibility Testing - last updated 22 March 2025 | Result
Boulderoid v1.15 | Screwed up rendering (unrecognisable)
DOOM | Screwed up rendering (recognisable)
Epic Pinball | NOTHING
Jazz Jackrabbit | MOSTLY GOOD
Skyroads | GOOD
Tyrian | Screwed up rendering (recognisable)
Terminal Velocity | GOOD (very slow)
Duke Nukem 3D | GOOD (very slow)
Windows XP | Screwed up rendering (KINDA recognisable)